# Maryland Native Plant Society

### 2017 Fall Conference Handbook

Updated November 11, 2016

Maintain records of for evaluation of the conference!

Update the Conference Handbook Each Year

### General Task Responsibilities

| Task | Committee | Chapter | Contact Person |
| --- | --- | --- | --- |
| Arrange location |  | X | Sue Dingwell |
| Arrange caterer |  | X | NCTC |
| Arrange speakers | X | X | Shirley Gay |
| Arrange field trips | X | X | Sue Dingwell |
| Create registration brochure | X |  | TBD |
| Create flyers/PR | X | X | TBD |
| Accept registrations | X |  | Karyn Molines |
| Send confirmations | X |  | Karyn Molines |
| Prepare conference packets Local information brochures | X | X | TBD |
| Pay expenses | X | X | MNPS |

# Funding the Conference

### SAMPLE Budget (feel free to change, then update the sums)

| EXAMPLE | PROPOSED | Purpose |
| --- | --- | --- |
| $600 | $2626 | Rental Fees (Auditorium) |
|  | $200 | AV |
|  | $55x2=$100 | Rental Fee: 8-person seminar (one per day) |
| $600 | $334x2=$668 | Rental Fees: 14-person seminar (one per day) |
|  | $697*8=$5,576 | Rental Fees: classroom (four per day) |
| $500 | $250*3=$750 | Speaker Honorarium |
|  | $1000 | Speaker Travel |
|  | $208x3=624 | Speaker Room & Board (includes spouse) |
| $100 | $300x20=$6000 | Field Trip Leader Room & Board |
| $325 | In R&B $$ | Breakfast |
| $225 | In R&B $$ | Break food |
| $750 | In R&B $$ | Lunch |
| $800 | In R&B $$ | Dinner |
|  | NA | Cash Bar |
| $500 | ? | Brochure Printing |
| $500 | ? | Postage (outside of mailing with Marilandica) |
| $50 | ? | Phone calls |
| $100 | ? | Transportation |
| $100 | NTCT | Name tags |
| $50 | ? | Registration Packet |
| $4600.00 | $18,358 | Total Expenses |
| Income |  |  |
| $3850 | $10,450 | Member Registration ($95/person) (110 people) |
| $325 | $1,650 | Nonmember Registration ($110/person) (15 people) |
| $900 | $4,400 | After August 1: Members $110 (40) |
| $325 | $1,875 | After August 1: Nonmember ($125/person) (15 people) |
| $325 | $750 | Students ($50/person) (15 people) |
| $200 |  | Conference Donations |
| $5925.00 | $19,125 | Total Income |

# Time line

### By August 1, 2016

- Determine who is on the Conference Committee	Done

- Develop local conference committee and volunteer contacts	Done

- Determine location	Done

- Develop theme	Done

- On Web Site – Save the Date; Developing Details	Karyn, Sue

- Create list of local accommodations	NCTC

### By December 1, 2016

- Confirm speakers’ availability	Shirley, Lori

- Submit Ideas for Workshops, Field Trip Locations & Leaders	Everyone Submit to Sue

### By February 1, 2017

- Flyer in Marilandica, VNPS newsletters

- Finalize Speaker Information	Shirley, Lori

  - Please complete Speaker Information Form

- Finalize Field Trip & Workshops & Leaders	Carrie, Marney, Margaret

  - Please complete Field Trip and Workshop Leader Information Form

- Finalize facility needs

- Determine facility payment schedule	Karyn/MNPS

### By March 1, 2017

- Complete Web Site Updates	Karyn, Sue

  - Agenda

  - Housing Details

  - Field Trips & Workshop Descriptions

- List of hotels on web site (optional)	 (NCTC)

### By March 15

General

Speakers

- Confirm speakers and field trip leaders

- Prepare abstract for publicity (optional)

Publicity

- Open registration on web site	Karyn

- Create a general flyer for posting and distributing

- Send out an email reminder to members 	Karyn, VNPS, WVNPS

- Send PR to papers, nature centers, etc	MNPS, VNPS, WVMNPS

# By July 1	CDay – 60 (at the latest)

General

- Web Site Updates as needed	Karyn, Sue

Registration

- Keep in touch about the numbers for catering, field trips, and workshops	Alan/Karyn

- Send out confirmation to registrants	Karyn

Publicity

- Send out an email reminder (Early Bird Deadline)	Karyn, VNPS, WVNPS

- Registration brochure or postcard (optional)

- Registration in Marilandica (optional)

- Brochure mailed to expired members, as well as multi-packs to our distribution sites. (optional)

Speakers, Field Trip & Workshop Leaders

- Confirm attendance of significant other	Shirley, Sue et al

- Confirm address, phone, and email. Submit for Complimentary membership	Shirley, Sue et al

- Produce handouts on topic (optional)

Caterers

- ** Determine caterer (see section on catering)	NCTC

- ** Determine menu	NCTC

- ** Determine time of food delivery	NCTC

- Arrange for payments	Karyn/MNPS

# By August 15	CDay – 45

Registration

- Maintain information on registrants	Karyn

- Finalize field trip & workshop participants	Karyn

- Provide preliminary registration, housing & meal numbers to facility	Alan/Karyn

Publicity

- Send out an email reminder 	Karyn

- Send PR to papers, nature centers, etc

# By September 7	CDay – 30

Email Final confirmation of registration

- Field Trip / Workshops 	Karyn

- Housing Selection	Karyn

# Week before conference	CDay – 7

Registration

- Provide final on registration, housing & meal numbers to facility	Alan/Karyn

- Create list of pre-registered for registration table	Karyn

- Create a list of people who have informed us that they will pay at the door	Karyn

- Include information on who receives complimentary registration 	Karyn

Late Registration

- Check the Post Office Box Friday for last minute registrations.	MNPS

- Have Registration forms and cash for on-site registrations

Name tags

- Indicate whether registrants have ordered vegetarian or non-vegetarian lunches	N/A

- Indicate whether they have paid for attending the social.	N/A

- Create name tags.	Karyn & NCTC

Caterers

- ** Provide final number and provide directions for where to deliver food	Karyn & NCTC

- ** Request check if payment must be made prior to or on the day of the conference

Field trips for Saturday afternoon and for Sunday

- Sign up sheets	Karyn

- Maps and/or directions

- Plant lists or information

Raffle, Native Treasures Sale or Silent Auction

- Forms for items

- Sales log

- Where and when will they be dropped off

Conference Handouts (optional)

- Agenda

- Field trip info

- Evaluation form

- Speaker handouts

- A thank you sheet with thanks to donors and copies of business cards of participating businesses

- Local or regional information

- Some info about MNPS, including a “teaser” about upcoming events

- A couple sheets of paper for notes with MNPS logo (optional)

- List of participants who’ve signed up for the conference (optional)

# Conference Weekend Sept. 29-Oct. 1, 2017

- Have cash on hand at the registration and sales table; have receipts ready to hand out.

- For Registration Table have: pens, pencils, markers, tape, stapler, paper	Karyn

- Copies of the list of pre-paid registrants and a list of those who will pay at the door.	Karyn

Parking Volunteers

- ** Place directional signs for parking	NCTC

- ** Place directional signs for getting to room (conference & social)	NCTC

Set up	Friday

- Those setting up must arrive ½ hour before event starts

- Tables for: registration desk; sales; general information; displays

- Caterer tables

- AV set up	NCTC

- Road and Parking signs	NCTC

- Set up Silent Auction/Sales

Facility (Workshop) Volunteers

- Audio/visual support

- Time keeper

- Photograph speakers & presenters

- Herd people back into the room at end of break (half-day workshops)

Field Trip Volunteers (half & full-day)

- Copies of the participant lists for each trip.	Karyn

At least one volunteer per trip to:

- Double check registration at site

- Record plants seen

- Take photos of the group

Social Events

- ** Arrive 4:30 to greet caterers

- Those setting up must arrive early—perhaps skipping the field trips

- Set up a greeting table	NCTC

- Table for sales & literature

- Silent Auction

- Announce start of speaker

Food

- Breakfast	NCTC

- Morning snack	NCTC

- Box lunch	NCTC

- Dinner	NCTC

# CDay + 7

After the Conference

- Write thank you letters to speakers & volunteers

- Provide Membership Secretary with speakers’ addresses for Complimentary memberships

- Submit all receipts for reimbursement

- Write a brief summary for Marilandica  and the archives

# Fall Conference Planning Form

Chapter Conference Co-Chair: Alan Ford <amford@acm.org>

Committee Members:  Karyn Molines <karyn.molines@gmail.com>,

Carrie Blair <horseblanketcb@yahoo.com>,

Shirley Wilson Gay shirleywg@me.com

Emily Grafton <egrafton@gmail.com>,

Karoline Oldham <karoline.a.oldham@gmail.com>,

Lori Bowes <loribowes@gmail.com>,

MarneyB <marneyb@earthlink.net>,

Nancy Vehrs <nvehrs1@yahoo.com>,

Rodney Dever <rodneydever@comcast.net>,

Sally Anderson <rccsca@comcast.net>,

"Steven D. Mace" <sdmace@frontiernet.net>,

Suzanne Dingwell <sue@dingwell.net>

Conference Title: Nature Knows No Boundaries

Theme of Conference:	Tri-state Connections

Secondary Theme:

Date:	Sept. 29-Oct. 1	Time: See schedule

Place:	National Conservation Training Center, Shepherdstown, WV

Room: varies

Rental Fee: See proposed budget

Saturday Speaker: (Complete a speaker form)

Place: Auditorium	Room:

Time:

Reg Fee: included in reg fee	Rental Fee: included in conf. rental

Saturday Social

Place: Bar & Campfire	Room:

Time:

Reg Fee: TBD, Cash Bar	Rental Fee: included in conf. rental

Event or Entertainment: (Complete a speaker form as necessary): Kevin Dodge

# Time Frame of Conference

| EXAMPLE | PROPOSED ACTIVITY | TASK |
| --- | --- | --- |
| FRIDAY |  |  |
| 12:00-4:00 | Field Trips |  |
| 4:00-5:30 | Registration |  |
| 5:30-6:30 | Social, Cash Bar |  |
| 6:30-7:30 | Dinner |  |
| 7:30-8:30 | Speaker |  |
| SATURDAY |  |  |
| 7:30-8:30 | Registration | Silent Auction Set-up |
|  | Field Trip Organization |  |
|  | Box Lunch pick up for Full-day trips |  |
| 9:00-4:30 | Full day field trips | 6-8 options |
| 9:00-12:00 | Half Day Workshops & Trips | 6-8 options |
| 12:00-1:00 | Lunch for Half Day |  |
| 1:00-4:00 | Half Day Workshops & Trips | 6-8 options |
| 5:30-6:30 | Social, Cash Bar |  |
| 6:30-7:30 | Dinner |  |
| 7:30-8:30 | Speaker |  |
| 8:30-10:00 | Campfire, Social, Speaker | Silent Auction Break down |
| SUNDAY |  |  |
| 7:30-8:30 | Field Trip Organization |  |
|  | Box Lunch pick up for trips |  |
| 9:00-12:00 | Half Day Workshops & Trips | 15-20 options |

# Registration

Registration Fees

Must cover food & room rental

Should cover speaker honorarium

Not a requirement to make money, try not to lose too much ($200 or so)

Conference cost is subsidized by the MNPS general fund

Optional: “Early Bird” registrations price discount?

Optional: Charge a late registration fee?

Optional: Charge an on-site registration surcharge?

As soon as possible start advertising date, place and general theme.

Registration fee should cover majority of expenses, but not be too expensive.

Member/nonmember differential should be enough to encourage membership.

Complementary Registrations must be factored into determining conference cost:

Room & Board provided on campus and Reg. fee waived for:

- Speakers & Spouses

- Field Trip leaders

Reg. fee only waived:

- Conference Committee

Registration Fee:

Early Bird: Members $95 Nonmembers $110 Student $50

After August 1: Members $115 Nonmembers $130 Student $50

Lunch included or separate? Included in housing fee; must pay if staying off campus

Social Events included in reg fee

Receiving Registrations

- All registrations should be acknowledged soon after being received. Information such as directions and lodging should be provided ASAP. This can be done by email, phone or mail.

- Registration log should be maintained by one person, and verified by a second person (Treasurer or Membership)

- Checks will be deposited by Treasurer

- All Registrations should be forwarded to Membership Chair to verify membership, record new members, and put non-members on our mailing list

# Facility

Will they provide…		If Not Who Will?

- Slide Projector

- LCD projector

- Laptop

- Overhead projector

- TV/VCR

- Amplification

- Lectern

- Chairs

- Tables: Need:

  - Registration: 	2

  - handouts:	2

  - posters/displays: 	2+

  - MNPS sales: 	2

  - Silent Auction 	3

  - food:	NCTC

Facility Questions

- Can the conference and social be at same location?

- Are there written rules?

- Who will need to sign contract?

- When is deposit required?

- When is final payment required?

- Can outside caterers be used?

- Inform facility that MNPS is a 501c3, and will charge a registration fee

- Trash and Recycling

- Set Up Assistance

- Clean Up Requirements

- Alcohol Policy

**Catering-

For 2017: Included in Room & Board; Those staying off campus must purchase meals via registration

Number of conference participants: Initial estimate: 75, perhaps as many as 125.

Number of social participants: Initial estimate: 40, perhaps more

When can we decrease, or increase the number?

Price quotes:

Breakfast (~$5/person)	Delivery Time:

Coffee, decaf, tea, sugar, cream

Fruit juice, water

Bagels, cream cheese, butter, jelly (volunteer could get these separately, depending on cost)

Muffins

Fruit (volunteer could get these separately, depending on cost)

Break (may include excess from breakfast) (~$4/person) 	Delivery Time:

Coffee, decaf, tea, sugar, cream

Fruit juice, water

Muffins

Fruit

Box Lunch (~$8/person)	Delivery Time:

Coffee, decaf, tea, sugar, cream

Fruit juice, water, sodas (volunteer could get these separately, depending on cost)

Sandwich (## vegan (hummus & veggies always a good choice)

Chips

Dessert

Saturday Social: 	Delivery Time:

Price quotes:

Number of social participants: 40

Can we decrease or increase the number? By what date?

Dinner options: (~$20/person)	Serving Time:

Coffee, decaf, tea, sugar, cream

Fruit juice, water, sodas (volunteer could get these separately, depending on cost)

Wine, beer (may charge extra for this i.e. cash bar)

Hors d’oerves

Meat entrée

Vegetarian entrée

Vegan salad, side dish (two or three different ones?)

Dessert

Other Questions

Delivery Fees

Deposit required date

Final payment requested date

Use of Non-disposable china and flatware

Clean up requirements

# Additional Support

Co-sponsors

Provide funding support (monetary or in-kind) including:

Paying speaker fees

Supplying food (morning, break, lunch, dinner)

Room rental fees (paying or waiving)

Evening Social Costs (rental, food, entertainment)

Friday Evening Social (rental, food, entertainment)

Mailing Costs or man-power

Program Supplies: Program, development & copying, Folders, Pens, Handouts, Notepads, Nametags

Ad or recognition in program

Partners

Speakers’ Organizations

Field Trip Sites

Field Trip Leaders

Other non-monetary contributions

Smaller ad and recognition in program

Caterers:

Ad in programs

Optional Activities

** Poster Session

** Raffle

** Native Treasures Sale

** Silent Auction

Sales (books, gee-gaws)

# Conference Speaker Information Sheet

Speaker Name

I will attend  (Conference    (Social    (Sat Field Trip    (Sun Field Trip

Dietary concerns

Title

Affiliation

Phone	Email

Address (for membership)

Guest (spouse, partner, friend) (receives complimentary registration, food & lodging)

Guest will attend  (Conference    (Social    (Sat Field Trip    (Sun Field Trip

Dietary concerns

Honorarium/Travel Expenses (On-site Lodging Provided gratis)

Biography: (max 75 words)

Title of Talk:

Description of Talk: (max 100 words)

# Field Trip & Workshop Leader Information Sheet

Make Copies as Necessary

Leader Name:

I will attend  (Conference  (Social       (Sat Field Trip    (Sun Field Trip

Dietary concerns:

Title

Affiliation

Phone	Email

Address (for membership)

Guest (spouse, partner, friend) (must pay conference registration & room & lodging)

Guest will attend  (Conference  (Social    (Sat Field Trip    (Sun Field Trip

Dietary concerns

Biography: (max 75 words)

Field Trip Information: (max 100 words)

( Saturday   Time:	 ( Sunday   Time:

( Would be willing to lead this event more than once during the weekend

Provide details:

( Offsite Location  ( Onsite: Indoor facility required  ( Onsite: Outdoors only

Minimum group size	Maximum group size

Special Instructions for Participants: (include level of difficulty if especially rigorous or especially easy)

Please Attach Directions:   (map links can be emailed)

# Fall Conference History

| Year | Location | Theme | Chairs |
| --- | --- | --- | --- |
| 1991 | Meadowside Nature Center Montgomery |  | Barbara Medina, Yvette Ogle, Nancy Ancel, Karyn Molines |
| 1992 | Ag. History Farm Park Montgomery | Restoring Their Habitats Beautifying our Yard | Barbara Medina, Kathy McCarthy |
| 1993 | Ag History Farm Park Montgomery |  | Kathy McCarthy, Gordon Brown |
| 1994 | Green Briar State Forest Allegany |  | Wilbur Rittenhouse, Jil Swearingen |
| 1994 | Adkins Arboretum Talbot | Spring Field Meeting | Wilbur Rittenhouse |
| 1995 | Soldier’s Delight Baltimore | Biodiversity of Barrens Communities | Jil Swearingen, Warren Steiner |
| 1996 | Horn Point EE Center Eastern Shore | Ecology of the Mid-Atlantic Coastal Plain | Jil Swearingen, Rod Simmons |
| 1997 | Frostburg Garrett | Allegheny Alliances and Communities | Mike Hollins, Lou Aronica |
| 1998 | Charles County Comm Coll Charles | Limits of Restoration | Karyn Molines |
| 1999 | Mount Saint Mary’s College Frederick | New Directions in Land Preservation | Rod Simmons, Lou Aronica |
| 2000 | Harford Glen EE Center Harford |  | Sam Jones, Harford Master Gardeners |
| 2001 | Talbot County Historic Soc. Talbot | Shaping Nature | Carol Jelich |
| 2002 | Patuxent Wildlife Research Ctr Prince Georges | Communities and Geology of the Fall Line | Rod Simmons, Meghan Tice |
| 2003 | National Conservation Training Center (WV) | Blue Ridge & Potomac Valley | Meghan Tice |
| 2004 | Calvert Marine Museum Calvert | Connecting Land, Water & The Bay | Karyn Molines, Carolyn Fulton, Lisa Garrett |
| 2005 | Oregon Ridge Baltimore | Urban & Suburban Forests | Louisa Thompson, Ann Lundy |
| 2006 | USM Shady Grove Montgomery | The Geology-Botany Connection | Linda Keenan, Melanie Choukas-Bradley |
| 2007 | Frostburg University Garrett | Climate Change: Global Effects, Local Impacts. Western Maryland’s Flora—At Risk? | Karyn Molines, Linda Keenan, Liz McDowell |
| 2008 | Smithsonian Environmental Research Center Anne Arundel | Ecological Communities of the Western Shores of the Chesapeake Bay | Karyn Molines |
| 2009 | Glade Valley Church of the Brethren Frederick | The Catoctin Mountains: Maryland’s Blue Ridge | Jim Gallion, Karyn Molines |
| 2010 | Chesapeake College Talbot | Biodiversity of Maryland’s Eastern Shore | Carol Jelich, Karyn Molines |
| 2011 | College of Southern Maryland Charles |  | Karyn Molines |
| 2012 | Towson University Baltimore | Preserving and Restoring Biodiversity in Developed Landscapes | Chris Partain, Vanessa Beauchamp, Kirsten Johnson |
| 2013 | Frostburg State University Garrett | The Threatened Natural Communities and Rare Plants of Maryland's Mountains | Sunshine Brosi, Liz McDowell |
| 2014 | Cecil College Cecil |  | Matt Bazar |
| 2015 | Salisbury University Wicomico | Shifting Sands: Coastal Plain Flora from Wetlands to Upland | Mark Holland, Karyn Molines |
| 2016 | University of Maryland, College Park Prince George’s | Forgotten Bogs and Pine Barrens | Karyn Molines, John Hall |
| 2017 | National Conservation Training Center (WV) | Nature Knows No Boundaries | Joint Sponsorship with VNPS, WVNPS |